## Project plan
| Please Complete Project Plan Below - Items in Italics are Transport Scotland MaaS risks | [6 empty] | Tasks
Basic Project Plan showing Milestones
Project Name:
Lead Applicant:
Fund Awarded:
Partners:
Stakeholders:
Project Name
|  | Year |  |  | 2020/21 |  |  | 2021/22 | [11 empty] | 2022/23 | [11 empty] | 2023/24
|  | Quarter |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
|  | Duration | Start | Finish | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01
Task Name
Phase | Pre Application | No of Days
| Pre-interest registration opens |  | 2020-11-01
| Pre-interest registration closes |  |  | 2020-12-01
| Full Briefing & Competition Opens |  | 2021-01-01
| Competition Closes |  |  | 2021-02-26
| Successful Notified Round 2 Contracts |  | 2021-04-30
1 | Project Start Up
Stakeholder Engagement
Match Funding Confirmed
Business Case
Complete Project Plan
Confirm Stakeholders
2 | Delivery/Implementation
Development of Solution
Solution Ready for Test
Develop Test Scripts & Plan
Solution Tested
Testing Sign off
3 | Project Mobilisation
Confirm Business Readiness
Complete Mobilisation
Marketing & Comms
Go/No Go Stakeholders
4 | Go Live/Evaluation
Commence Live Pilot Duration Timeline
Monitoring Period 1
Monitoring Period 2
Monitoring Period 3
5 | Project Closure
Pilot Closure Report
Lessons Learned
Please confirm start/end dates for each Project Task
If your project tasks are on track or scheduled to run overdue, please use the RAG status below:-
Green | Project schedule is on target
Amber | There are likely to be minor delays in the scheduled of up to 30 days
Red | There will be delays of greater that 30 days