

Dear Neighbour,

We are writing to provide you with an update of planned works on the Forth Replacement Crossing (FRC).

We have recently applied to Transport Scotland and have been granted permission to modify our working hours in two separate locations as follows:-

The first modification covers the night time working hours to construct the base of gantry G15 which is adjacent to the southbound carriageway of the A90, 200 metres south of Dunfermline Wynd.

The date and time for the erection of shutters for concrete for this base will be Thursday and Friday 12th and 13th of May commencing at 20:00hrs and working through to 06:00hrs the following morning on both dates. Concreting will be carried out during the day on Saturday14th May and the removal of the shutters will be carried out on Tuesday 17th May between 20:00 and 12:00 midnight.

In addition to the foregoing we have also received permission to work an extra hour, between 07:00 and 08:00 Monday to Saturday and 08:00 – 1800 on Sundays for a period of six weeks from Sunday15th May through to 20th June inclusive on the new structures which will extend the bridges at the new Ferrytoll gyratory.

The justification for this is to recover time created by the exceptional circumstances which culminated in the temporary closure of the Forth Road Bridge to Heavy Goods Vehicles

from December 2015 through to 20th February 2016 inclusive.

In all cases described above the works we will be carrying out will be low impact.

**The times indicated can be influenced by many factors and may change without warning near or during the time of execution. Also, the overall duration of each element may require to be extended in duration to achieve completion should unforseen circumstances be encountered.**

**Please accept our apologies for any disturbance our works have caused you to date. We will endeavour to keep you informed of these ongoing works in the vicinity of your residence through to completion of the Ferrytoll works in 2016.**

 **PTO**

**Should you wish to subscribe to receive updates on the works associated with the Ferrytoll junction please follow the guidelines on the website** [**www.frc-ferrytoll.info**](http://www.frc-ferrytoll.info)**.**

**For up to date information on the project please see Transport Scotland’s FRC project website** [**www.forthreplacementcrossing.info**](http://www.forthreplacementcrossing.info)**. Should you have any queries, please contact our email** **enquiries@forthreplacementcrossing.info** **or our Hotline on 0800 078 6910.**

**In addition, our Contact and Education Centre, located adjacent to the Forth Road Bridge offices on the south side of the existing Forth Road Bridge, is**

**manned 09:00hrs to 17:00hrs Monday to Thursday, 09:00hrs to 16:00hrs on**

**Fridays and 10:00hrs to 16:00hrs on Saturdays (through to December 2016 to deal with enquiries and to supply information. Additionally, access to the Exhibition room in the building is available at certain times.**

**For confirmation of all opening times please check the project website.**

Issued to – Residents adjacent to the works in Inverkeithing

Issue date –11th May 2016 Ref F94